## Pre-Production Summary
Project Name
Total Estimated Assets & Implementation Times | (See other sheets for breakdowns)
Total Model Time: | 102.4
Total Rigging and Animation Time: | 5.8
Total Scripting Time: | 25.1
Total VFX Time: | 22.4
Total SFX Time: | 26.6
Total UI Time: | 21.7
Total Time: | 204
Scale
Unit Size:
Notes:
Unknowns

## Models
Models | Category | Model Time | UV Map Time | Texture Time | LightingTime | Approval/Adjustment Time | Total Time For Model
Low-Res Models
ExtSwamp | Large | 2.5 |  | 3 | 0.3 | 1 | 6.8
IzbaInterior | Large | 6 |  | 4 | 0.5 | 2 | 12.5
RussianChimney | Large | 2 |  | 1 | 0.5 | 1 | 4.5
BabaYagaHut | Large | 8 |  | 6 | 1 | 0.5 | 15.5
[6 empty] | Total Low-Res Model Time: | 39.3
Medium-Res Models
Table1 | Medium | 0.5 |  | 0.3 | 0.2 | 0.2 | 1.2
Table2 | Medium | 0.2 |  | 0.1 | 0.2 | 0.2 | 0.7
EndTable | Medium | 0.2 |  | 0.1 | 0.2 | 0.2 | 0.7
Bench | Medium | 0.4 |  | 0.2 | 0.2 | 0.2 | 1
LoomWheel | Medium | 3 |  | 1 | 0.5 | 0.2 | 4.7
BristleBroom | Medium | 1 |  | 0.5 | 0.2 | 0.2 | 1.9
Cot | Medium | 2 |  | 2 | 0.2 | 0.2 | 4.4
Chair | Medium | 2 |  | 1 | 0.2 | 0.2 | 3.4
ChairBroken | Medium | 0.3 |  | 0.2 | 0.3 | 0.2 | 1
Stool | Medium | 0.5 |  | 0.5 | 0.2 | 0.2 | 1.4
Rug | Medium | 0.2 |  | 2 | 0.2 | 0.2 | 2.6
Samovar | Medium | 2 |  | 0.5 | 0.2 | 0.2 | 2.9
TreeBumps | Medium | 0.3 |  | 0.5 | 0.2 | 0.2 | 1.2
TreeVariants | Medium | 1 |  | 1 | 0.4 | 0.2 | 2.6
MushroomBasketBackpack1 | Medium | 0.5 |  | 1 | 0.2 | 0.2 | 1.9
[6 empty] | Total Medium-Res Model Time: | 31.6
High-Res Models
HerbParsley | Small | 0.3 |  | 0.5 | 0.2 | 0.2 | 1.2
HerbGarlic | Small | 0.8 |  | 0.8 | 0.2 | 0.2 | 2
HangingString | Small | 0.5 |  | 0.2 | 0.2 | 0.2 | 1.1
Pot1 | Small | 0.2 |  | 0.5 | 0.2 | 0.2 | 1.1
Pot2 | Small | 0.1 |  | 0.5 | 0.2 | 0.2 | 1
Bowl1 | Small | 0.3 |  | 0.3 | 0.2 | 0.2 | 1
Bowl2 | Small | 0.3 |  | 0.3 | 0.2 | 0.2 | 1
Bowl3 | Small | 0.3 |  | 0.3 | 0.2 | 0.2 | 1
Plate1 | Small | 0.3 |  | 0.3 | 0.3 | 0.2 | 1.1
Plate2 | Small | 0.2 |  | 0.2 | 0.2 | 0.2 | 0.8
Plate3 | Small | 0.2 |  | 0.2 | 0.2 | 0.2 | 0.8
Vase1 | Small | 0.3 |  | 0.3 | 0.2 | 0.2 | 1
Vase2 | Small | 0.2 |  | 0.2 | 0.2 | 0.2 | 0.8
Dish Shelf | Small | 1 |  | 0.5 | 0.2 | 0.2 | 1.9
Cutting Board | Small | 0.3 |  | 0.3 | 0.2 | 0.2 | 1
Shawl | Small | 0.6 |  | 1.5 | 0.3 | 0.2 | 2.6
Basket1 | Small | 0.5 |  | 0.5 | 0.2 | 0.2 | 1.4
Basket2 | Small | 0.5 |  | 0.5 | 0.3 | 0.2 | 1.5
Rotten Apple | Small | 0.3 |  | 0.4 | 0.5 | 0.2 | 1.4
Oil Lamp Base | Small | 1.5 |  | 0.5 | 0.3 | 0.2 | 2.5
Oil Lamp Shell | Small | 0.3 |  | 0.2 | 0.2 | 0.2 | 0.9
GrassTuft1 | Small | 0.2 |  | 0.3 | 0.2 | 0.2 | 0.9
GrassTuft2 | Small | 0.2 |  | 0.3 | 0.2 | 0.2 | 0.9
GrassTuft3 | Small | 0.5 |  | 0.5 | 0.2 | 0.2 | 1.4
GrassTuft4 | Small | 0.4 |  | 0.4 | 0.2 | 0.2 | 1.2
[6 empty] | Total High-Res Model Time: | 31.5
[6 empty] | Total Model Time: | 102.4

## Rigging and Animation
Model To Animate | Category | Rig Time | Animation Time | Implement Time | Test Time | Approval/Adjustment Time | Total Time For Animation
Characters
BabaYagaHut | Large | 3 | 1 | 0.5 | 0.3 | 1 | 5.8
[6 empty] | Total Character Animation Time: | 5.8
[6 empty] | Total Rig & Animation Time: | 5.8

## Scripts
Scripts | Category | Coding Time | Implement Time | Test Time | Approval/Adjustment Time | Total Time For Script
Player
PlayerMovement | Medium | 2 | 0.5 | 0.5 | 1 | 4
CameraControl | Small | 1 | 0.3 | 0.2 | 1 | 2.5
Jump | Small | 1 | 0.3 | 0.2 | 2 | 3.5
[5 empty] | Total Player Script Time: | 10
Game Events
GameReset | Small | 1 | 0.3 | 0.2 | 0.5 | 2
PlayerDeath | Small | 1 | 0.2 | 0.1 | 0.5 | 1.8
CollectItem | Medium | 2 | 0.5 | 0.5 | 1 | 4
[5 empty] | Total Events Script Time: | 7.8
Rendering
CullingObjects | Small | 1 | 0.2 | 0.2 | 1 | 2.4
TexReplacer(?) | Medium | 2 | 0.4 | 0.5 | 2 | 4.9
[5 empty] | Total Rendering Script Time: | 7.3
[5 empty] | Total Script Time: | 25.1

## VFX
VFX | Category | Art/Script Time | Implementation Time | Test Time | Approval/Adjustment Time | Total Time For VFX
Camera
Shake | Medium | 0.3 | 1.5 | 0.3 | 1 | 3.1
Collect | Small | 0.3 | 1 | 0.2 | 1 | 2.5
Death | Medium | 0.3 | 1 | 0.3 | 1 | 2.6
[5 empty] | Total Camera VFX Time: | 8.2
Environmental
Fog | Large | 2 | 2 | 0.4 | 1 | 5.4
[5 empty] | Total Environmental VFX Time: | 5.4
Event
WoodCrack | Small | 1 | 1 | 0.5 | 0.5 | 3
DustPoof | Small | 1 | 1 | 0.5 | 0.5 | 3
CollectSparkle | Small | 1 | 1 | 0.3 | 0.5 | 2.8
[5 empty] | Total Event VFX Time: | 8.8
[5 empty] | Total VFX Time: | 22.4

## SFX
SFX | Category | Recording/Editing Time | Implementation Time | Test Time | Approval/Adjustment Time | Total Time For SFX
Player
Damage | Small | 0.3 | 1 | 0.2 | 0.5 | 2
Jump | Small | 0.3 | 1 | 0.2 | 0.5 | 2
Landing | Small | 0.3 | 1 | 0.2 | 0.5 | 2
HeavyLanding | Small | 0.3 | 1 | 0.2 | 0.5 | 2
Death | Medium | 1 | 1 | 0.2 | 1 | 3.2
[5 empty] | Total Player SFX Time: | 11.2
Environmental
BackgroundCreaks | Large | 2 | 1 | 0.5 | 1 | 4.5
BabaYagaHutStomp | Medium | 0.5 | 2 | 0.5 | 1 | 4
[5 empty] | Total Environmental SFX Time: | 8.5
Event
WoodCrack | Small | 0.5 | 1 | 0.3 | 0.5 | 2.3
DustPoof | Small | 0.5 | 1 | 0.3 | 0.5 | 2.3
CollectSparkle | Small | 0.5 | 1 | 0.3 | 0.5 | 2.3
[5 empty] | Total Event SFX Time: | 6.9
[5 empty] | Total SFX Time: | 26.6

## UI
UI | Category | Art/Scripting Time | Implementation Time | Test Time | Approval/Adjustment Time | Total Time For UI
Camera
CrackScreen | Medium | 2 | 2 | 0.2 | 0.5 | 4.7
Collectable | Small | 1 | 1 | 0.2 | 0.5 | 2.7
FadeScreen | Small | 0.3 | 2 | 0.2 | 1 | 3.5
[5 empty] | Total Camera UI Time: | 10.9
Front End
TitleScreen | Large | 2 | 1 | 0.5 | 1 | 4.5
[5 empty] | Total Front End UI Time: | 4.5
Pause
PauseMenu | Large | 3 | 2 | 0.3 | 1 | 6.3
[5 empty] | Total Pause UI Time: | 6.3
[5 empty] | Total UI Time: | 21.7